Source: Information Management and Telecommunications (IM&T) Risk Management Handbook, Information Management and Telecommunications Project Office, The Pentagon Renovation Project Office, 100 Boundary Channel Drive, Arlington, VA 22202-3712, Draft, 1999.  [IM&T 99]

Risk Checklist

|  | Risk Factors | Low Risk Cues | Medium Risk Cues | High Risk Cues |
| --- | --- | --- | --- | --- |
| 1 | Project fit to Customer Organization | Directly supports customer organization mission and goals | Indirectly impacts one or more goals of customer | Does not support or relate to customer organization mission or goals |
| 2 | Project fit to provider Organization | Directly supports provider organization mission and goals | Indirectly impacts one or more goals of provider | Not support |
| 3 | Customer perception | Customer expects this organization to provide this product | Organization is working on project not expected by customer | Project is mismatch with prior products or services of this organization |
| 4 | Work flow | Little or no change to work flow | Will change some aspect or have small impact on work flow | Significantly change the work flow or method of organization |
| 5 | Goals conflict | Goals of projects are supportive of or complimentary to each other | Goals of projects do not conflict but provide little direct support | Goals of projects are in conflict, either directly or indirectly |
| 6 | Resource conflict | Projects within the program share resources without any conflict | Projects within the program schedule resources without any conflict | Projects within the program often need the same resources at the same time (or compete for the same budget) |
| 7 | Customer conflict | Multiple customers of the program have common needs | Multiple customers of the program have different needs, but do not conflict | Multiple customers of the program are trying to drive it in different directions |
| 8 | Directorship | Program has active major project director who coordinates projects | Program has person or team responsible for the program, but unable to spend enough time to lead effectively | Program has no director or major project director concept is not in use |
| 9 | Major project director experience | Major project director has deep experience in the domain | Major project director has some experience in the domain, is able to leverage subject experts | Major project director is new to the domain |
| 10 | Definition of the program | Program is well-defined, with a scope that is manageable by the organization | Program is well-defined but unlikely to be handled by this organization | Program is not well defined or carries conflicting objectives in the scope |
| 11 | Political Issues | No particular politically-driven choices being made | Project has several politically motivated decisions, such as using a vendor selected for political reasons, rather than qualifications | Project has a variety of political influences or most decisions are made behind closed doors |
| 12 | Convenient date | Date for delivery has been set by reasonable project commitment process | Date is being partially driven by need to meet marketing demo, trade show, or other mandate not related to technical estimate | Date is totally driven by need to meet marketing demo, trade show, or other mandate; little consideration of project team estimates |
| 13 | Use of Attractive Technology | Technology selected has been in use for some time | Project is being done in sub-optimal way, t leverage the purchase or development of new technology | Project is being done as a way to show a new technology or as a n excuse to bring new technology into the organization |
| 14 | Short term solution | Project meets short term need without serious compromise to long-term outlook | Project focussed on short-term solution to a problem with little understanding of what is needed in the long term | Project has been explicitly directed to ignore the long term outlook and focus thee short term deliverable |
| 15 | Organizational stability | Little or no change in management or structure expected | Some management change or reorganization expected | Management or organization structure is continually or rapidly changing |
| 16 | Organizational roles and responsibilities | Individuals throughout the organization understand their roles and responsibilities and those of others | Individuals understand their roles and responsibilities, but are unsure who is responsible for work outside their immediate group | Many in the organization are unsure or unaware of who is responsible for many activities of the organization |
| 17 | Policies and standards | Development policies and standards are defined and carefully followed | Development policies and standards are in place, bur are weak or nor carefully followed | No policies or standards, or they are ill-defined and unused |
| 18 | Management support | Strongly committed to success of project | Some commitment, but not total | Little or no support |
| 19 | Executive involvement | Visible and strong support | Occasional support, provides help on issues when requested | No visible support; no help on unresolved issues |
| 20 | Project Objectives | Verifiable project objectives, reasonable requirements | Some project objectives, measures may be questionable | No established project objectives or objectives are not measurable |
| 21 | User involvement | Users highly involved with project team, provides significant input | Users play minor roles, moderate impact on system | Minimal or no user involvement; little user input |
| 22 | User experience | Users highly experienced in similar projects; have specific ideas of how needs can be met | Users have experience with similar projects and have needs in mind | Users have no previous experience with similar projects; unsure of how needs can be met |
| 23 | User acceptance | Users accept concepts and details of system; process in place for user approvals | Users accept most of concepts and details of system; process in place for user approvals | Users do not accept any concepts or design details of system |
| 24 | User training needs | User training needs considered; training in progress or plan in place | User training needs considered; no training yet or training plan is in development | Requirements not identified or not addressed |
| 25 | User justification | User justification complete, accurate, sound | User justification provided, complete with some questions about applicability | No satisfactory justification for system |
| 26 | Project size | Small, non-complex, or easily decomposed | Medium, moderate complexity, decomposable | Large, highly complex, or not decomposable |
| 27 | Reusable components | Components available are compatible with approach | Components available, but need some revision | Components identified, need serious modification for use |
| 28 | Supplied components | Components available and directly usable | Components work under most circumstances | Components known to fail in certain cases, likely to be late, or incompatible with parts of approach |
| 29 | Budget size | Sufficient budget allocated | Questionable budget allocated | Doubtful budget is sufficient |
| 30 | Budget constraints | Funds allocated without constraints | Some questions about availability of funds | Allocation in doubt or subject to change without notice |
| 31 | Cost controls | Well established, in place | System in place, weak in areas | System lacking or nonexistent |
| 32 | Delivery commitment | Stable commitment dates | Some uncertain commitments | Unstable fluctuating commitments |
| 33 | Development schedule | Team agrees that schedule is acceptable and can be met | Team finds one phase of the plan to have a schedule that is too aggressive | Team agrees that two or more phases of schedule are unlikely to be met |
| 34 | Requirements stability | Little or no change expected to approved set (baseline) | Some change expected against approved set | Rapidly changing or no agreed-on baseline |
| 35 | Requirements completeness and clarity | All completely specified and clearly written | Some requirements incomplete or unclear | Some requirements only in the head of the customer |
| 36 | Testability | Product requirements easy to test, plans underway | Parts of product hard to test, or minimal planning being done | Most of product hard to test, or no test plans being made |
| 37 | Design difficulty | Well defined interfaces; design well understood | unclear how design, or aspects of design yet to be decided | Interfaces not well defined or controlled; subject to change |
| 38 | Implementation difficulty | Content is reasonable for this team to implement | Content has elements somewhat difficult for this team to implement | Content has components this team will find very difficult to implement |
| 39 | System dependencies | Clearly defined dependencies of the project and other parts of the system | Some elements of the system are well understood and planned; others are not yet comprehended | No clear plan or schedule for how the whole system will come together |
| 40 | Response or other Performance factors | Readily fits boundaries needed; analysis has been done | Operates occasionally at the boundary | Operates continuously at boundary levels |
| 41 | Customer service impact | Requires little change to customer service | Requires minor change to customer service | Requires major changes to customer service approach or offering |
| 43 | Pilot approach | Pilot site (or team) available and interested in participating | Pilot needs to be done with several sites (who are willing) or with one who needs much help | Only available pilot sites are uncooperative or in crisis mode already |
| 44 | Alternatives analysis | Analysis of alternatives complete, all considered assumptions verifiable | Analysis of alternatives complete, some assumptions questionable or alternatives not fully considered | Analysis not completed, not all alternatives considered, or assumptions faulty |
| 45 | Commitment process | Changes to commitments in scope, content schedule are reviewed and approved by all involved | Changes to commitments are communicated to all involved | Changes to commitments are made without review or involvement of the team |
| 46 | Quality assurance approach | QA system established, followed, effective | Procedures established, but not well followed or effective | No QA process or established procedures |
| 47 | Development documentation | Correct and available | Some deficiencies, but available | Nonexistent |
| 48 | Use of defined Development process | Development process in place, established, effective, followed by team | Process established, but not followed or is ineffective | No formal process used |
| 49 | Early Identification of defects | Peer reviews are incorporated throughout | Peer reviews are used sporadically | Team expects to find all defects with testing |
| 50 | Defect tracking | Defect tracking defined, consistent, effective | Defect tracking process defined, but inconsistently used | No procedure in place to track defects |
| 51 | Change control for work products | Formal change control process in place, followed, effective | Change control process in place, not followed or is ineffective | No change control process used |
| 52 | Physical facilities | Little or no modification needed | Some modifications needed; some existent | Major modifications needed, or facilities nonexistent |
| 53 | Tool availability | In place, documented, validated | Available, validated, some development needed (or minimal documentation) | Not validated, propriety, or major development needed; no documentation |
| 54 | Vendor support | Complete support at reasonable price and in needed time frame | Adequate support at contracted price, reasonable response time | Little or no support, high cost, and/or poor response time |
| 55 | Contract fit | Contract with customer has good terms, communications with team is good | Contract has some issues which could interrupt team work efforts | Contract has burdensome document requirements or causes extra work to comply |
| 56 | Disaster recovery | All areas following security guidelines; data backed up; disaster recovery system in place; procedures followed | Some security measures in place; backups done; disaster recovery considered, but procedures lacking or not followed | No security measures in place; backup lacking; disaster recovery not considered |
| 57 | PM approach | Product and process planning and monitoring in place | Planning and monitoring need enhancement | Weak or nonexistent planning and monitoring |
| 58 | PM experience | PM very experienced with similar projects | PM has moderate experience with different types of projects | PM has no experience with this type of project or is new to project management |
| 59 | PM authority |  | Has line management or official authority that enables project directorship effectiveness | Has little authority from location in the organization structure and little power to influence decision making resources |
| 60 | Support of the PM | Complete support by team and of management | Support by most of team, with some reservations | No visible support; manager in name only |
| 61 | Team member availability | In place, little turnover expected; few interrupts for fire fighting | Available, some turnover expected; some fire fighting | High turnover, not available; team spends most of time fighting fires |
| 62 | Mix of team skills | Good mix of disciplines | Some disciplines inadequately represented | Some disciplines not represented |
| 63 | Team communication | Clearly communicates goals and status between the team and rest of organization | Team communicates some of the information some of the time | Rarely communicates clearly within the team or to others who need to be informed |
| 64 | Application engineers | Extensive experience in team with projects like this | Some experience with similar projects | Little or no experience with similar projects |
| 65 | Experience with Application Area (Domain) | High experience | Average experience | Low experience |
| 66 | Experience with project tools | High experience | Average experience | Low experience |
| 67 | Experience with project process | High experience | Average experience | Low experience |
| 68 | Training of team | Training plan in place, training ongoing | Training for some areas not available or training planned for the future | No training plan or training not readily available |
| 69 | Team spirit and attitude | Strongly committed to success of project; cooperative | Willing to do what it takes to get the job done | Little or no commitment to the project; not a cohesive team |
| 70 | Team productivity | All milestones met, deliverables on time, productivity high | Milestones met, some delays in deliverables, productivity acceptable | Productivity low, milestones not met, delays in deliverables |
| 71 | Technology match to project | Technology planned for project is good match to customers and problem | Some of the planned technology is not well suited to the problem or customer | Selected technology is a poor match to the problem or customer |
| 72 | Technology experience of team | Good level of experience with technology | Some experience with the technology | No experience with the technology |
| 73 | Availability of technology expertise | Technology experts readily available | Experts available elsewhere in organization | Will need to acquire help from outside organization |
| 74 | Maturity of technology | Technology has been in use in the industry for quite a while | Technology is well understood in the industry | Technology is leading edge, if not “bleeding edge” in nature |
| 75 | Design complexity | Easily maintained | Certain aspects difficult to maintain | Extremely difficult to maintain |
| 76 | Support personnel | In place, experienced, sufficient in number | Missing some areas of expertise | Significant discipline or expertise missing |
| 77 | Vendor support | Complete support at reasonable price and in the needed time frame | Adequate support at contracted price, reasonable response time | Little or no support, high cost, and/or poor response time |